## Work plan 2022
Draft
Work plan for implementing the EITI in Ukraine in 2023 |  |  |  |  | Approved by:
Monitoring and evaluation
1) New monitoring results every two months -> National Secretariat or responsible member of EITI MG
2) Discussion of the implementation process at each meeting of the EITI MG
3) The responsible parties will draw up their work plans and submit them for inclusion in the overall EITI Work Plan
Objectives | Relevant EITI provision | Activities | Expected outputs (actions) | Expected outcomes | Responsible agency | Deadline | Source of funding | Amount, USD $
1. National priority: imroving transparency and data disclosure in extractive industries
1.1. Publication (drafting) of Ukraine's EITI Report for 2022
| EITI requirement 1.5 c (II) | The EITI MG reviews the scope and content of the EITI reporting, including plans to address technical aspects of reporting such as data completeness and reliability | The Terms of Reference (TOR) for the Independent Administrator have been developed taking into account the decision taken | Ensuring that the EITI Report fully meets the needs of the country and complies with the new EITI Standard requirements and ammendments made to Ukraine's legislation | Ministry of Energy, the EITI MG, National Secretariat; | February 2022 | Does not require additional financing | 115000
| EITI requirement 1.4b | The Terms of Reference (TOR) for Independent Administrator have been approved by the EITI MG | TOR for the Independent Administrator | Ensuring that the context part of the Report and the Payment Reconciliation part of the Report are prepared carefully and the Independent Administrator understands the task | Ministry of Energy, the EITI MG, National Secretariat; | March 2023 | Does not require additional financing
| EITI requirement 1.4b (iv) | Selection of the Independent Administrator; selection has been approved by the EITI MG | A contract has been concluded with the Independent Administrator | Provision of the basis for drafting the Report | Ministry of Energy, the EITI MG, National Secretariat; | May 2023 | Does not require additional financing
| EITI requirements 2.1-6.3 | The Independent Administrator collects data for the Report from companies and governments | Contextual part of the Report, reconciliation of payments | Ensuring the completeness of the Report | Ministry of Energy, Ministry of Finance, State Service of Geology and Mineral Resources, other central executive authorities, companies and state enterprises | September 2023 | Ministry of Energy
| EITI requirement 5.2 | The Independent Administrator verifies the data received from the reporting institutions and drafts the Report | Payment reconciliation completed | Reconciliation | Ministry of Energy, STS, companies, Independent Administrator; | October 2023 | Ministry of Energy
| EITI requirements 5.3. and 6 | The EITI MG approves the ninth EITI Report for 2022 | The Ninth EITI Report published | Better informed public debate on extractive industries | Ministry of Energy, the EITI MG, National Secretariat; | November 2023 | Ministry of Energy
1.2 Integration of the EITI into government systems
Creation of conditions for a legislative and regulatory framework harmonized with the EITI, the basis for greater transparency in the industry is laid at the level of law and by-laws |  | By-laws to the Law of Ukraine "On Ensuring Transparency in Extractive Industries" (legal support, etc.), namely CMU Resolution #838, have been updated | Updated by-laws to the Law of Ukraine "On ensuring transparency in extractive industries" adopted | The EITI implementation is embedded at the level of law and by-laws, the EITI reporting is mandatory | Ministry of Energy, National Secretariat | December 2023 | ???
|  | Provisions on the EITI MG have been updated in accordance with the Law of Ukraine "On Amendments to Certain Legislative Acts of Ukraine on Ensuring Transparency in Extractive Industries" # 1974, dated 16.12.2021 | Provisions on the EITI MG have been updated |  | Ministry of Energy, the EITI MG | June-August 2023 | Does not require additional financing
| EITI Requirement 2.4 | Publication (after the end of martial law) of information on the material conditions of subsoil use agreements (PSA, concession, JVA, and other extracting contracts) signed by December 2022; and full publication of agreements signed from 2022 | Contracts/material conditions of contracts published on the Ministry of Energy's website | Contracts/material conditions of contracts published on the website of the Ministry of Energy | Ministry of Energy, National Secretariat of the EITI | 6 months after the end of martial law | Does not require additional financing | N/A
Improving operation of the system for automated data collection and processing of the EITI Report "EITI Reports Submission and Analysis Electronic System" (online platform) MVP for data collection and processing of the EITI Report | EITI requirement 7.2 | Carrying out activities on integration and exchange of data between the Ministry of Energy and Central Executive Authorities. Integration of the online EITI system with other online products (State Taxt Service and State Service of Geology and Mineral Resources of Ukraine) | Data collection and processing through the online platform has been automated | Reduction of expenditures for the Independent Administrator, improved data openness and availability. Participation of the Ministry of Energy as a beneficiary of the new GIZ project "Good governance through GovTech and Transparency in Ukraine" | GIZ, National Secretariat, Ministry of Energy, the EITI MG | Until December 2023 | GIZ, Ministry of Energy, EBRD
|  | Cooperation with the German Society for International Cooperation (GIZ) on the project "Good Governance through GovTech and Transparency in Ukraine" | MoU signed within the framework of new GIZ project "Good governance through GovTech and Transparency in Ukraine"
Implementation of the EITI in 2023 |  | Implementation of the Action Plan for ensuring the functioning of the "Electronic System for Submission and Analysis of EITI Reporting" (EITI Portal) for 2023-2025. Analysis of the updated EITI Standard in the event of its adoption at the Global EITI Conference in June 2023, translation, drafting of proposals for amendments to the current legal framework. |  |  | Members of the EITI MG, Secretariat, Ministry of Energy, the EITI MG
Disclosure of beneficial owners | EITI requirement 2.5 | According to Requirement 2.5 c) of the 2019 EITI Standard: As of 1 January 2020, it is required that implementing countries request, and companies publicly disclose, beneficial ownership information. | A report on monitoring the disclosure of information about beneficial owners has been published | The system of disclosure of data on beneficial owners has been improved. Activities/discussions were held on the development of the beneficial owner verification system | Members of the the EITI MG (Olexii Orlovskyi) | By the end of 2023 | Does not require additional financing | N/A
Ensuring the inclusion of EITI in key government documents aimed at the implementation of reforms and fight against corruption |  | Inclusion of the obligation to implement the EITI in such key initiatives and documents as the "Open Government Partnership", the Government's Anti-Corruption Strategy, the Action Plan for Implementation of the Association Agreement with the EU, etc. shall contribute to greater responsibility of all stakeholders and the government, in particular, for the purpose of sustainable implementation of the EITI. Therefore it is necessary to work with all stakeholders in order to include the EITI into the key commitments of our country in the framework of reforms and anti-corruption activities. To include proposals on the EITI in the action plan of "Open Government Partnership" for 2023-2024. | The EITI is part of the key documents within the framework of Ukraine's international obligations in relation to reforms and anti-corruption activities. | The EITI is part of the government's overall plans for reforms and anti-corruption activities. | National Secretariat, Ministry of Energy, the EITI MG | During the year | Does not require additional financing | N/A
|  | Proposals to the Ministry of Foreign Affairs regarding amendments to the List of central bodies of executive power and other state bodies responsible for fulfilling obligations arising from Ukraine's membership in international organizations, approved by Resolution of the Cabinet of Ministers of Ukraine of September 13, 2002 # 1371 | Amendments made to the CMU Resolution #1371 of September 13, 2002 | The EITI is included in the List of central bodies of executive power, other state bodies responsible for fulfilling obligations arising from Ukraine's membership in international organizations | Ministry of Energy, members of the the EITI MG | _"_
|  | Translation of the new edition of the EITI Standard into Ukrainian |  |  | International Renaissance Foundation | July 2023 |  | 700
1.3. Other measures within the framework of EITI implementation in Ukraine
Progress report | EITI requirements 7.4 and 8.4 | Pursuant to clauses 7.4 and 8.4, the EITI MG shall publish an annual Progress Report following appropriate consultations. | The Annual Progress Report approved by the EITI MG and published | Ensures compliance with the requirements of the Standard | The EITI MG, Ministry of Energy, National Secretariat; | Until July 1, 2023 | Does not require additional financing | N/A
| EITI requirements 7.4 and 8.5 | Translation of the 2022 Progress Report into English | The Annual Progress Report has been translated | The Annual Progress Report avalible in English. | The EITI MG, Ministry of Energy, National Secretariat; | October, 2023 | funded by the World Bank
Assessment of the EITI implementation process | EITI requirements 7.1 and 7.2 | The EITI MG shall agree on a clear policy regarding the data access, release and use. The EITI MG has agreed on an open data policy, but it is important to monitor the commitments made and progress achieved with regard to open data. Accordingly, an assessment of progress should be reflected in the annual Progress Report. | An evaluation has been carried out and reflected in the Annual Progress Report | The country's progress on the path to open data has been ensured | The EITI MG, Ministry of Energy, National Secretariat; | Until July 1, 2023 | Does not require additional financing | N/A
Adapted implementation of the EITI | Chapter 4. Article 1 | In connection with the military aggression of the Russian Federation, the EITI MG will consider the possibility of applying to the EITI Board with a request for an adapted implementation for 2023-2024. | A request for an adapted implementation has been submitted for consideration to the EITI Management Board | It is necessary for the successful completion of validation and obtaining the status of a country, which meets the EITI requirements | The EITI MG, Ministry of Energy, National Secretariat; | Until March 2023 | Does not require additional financing | N/A
Work plan | EITI requirement 1.5 | Annual review of the work plan in consultation with all stakeholders. | A work plan for 2023 has been developed | The work plan has been updated taking into account the goals defined by the EITI MG | The EITI MG, Ministry of Energy, National Secretariat; | March 2023 | Does not require additional financing | N/A
| EITI requirement 1.6 | Translation of the EITI Work Plan 2023 into English | A work plan for 2023 has been translated | A work plan for 2023 has been published | The EITI MG, National Secretariat; | October 2023 | funded by the World Bank
Improvement of the implementation process of the Transparency Initiative and drafting of the EITI Report | EITI requirement 1.5c (iv) | Discussion of the EITI MG regarding the implementation of EITI Report recommendations and validation and implementation of the new EITI Standard in case of its adoption at the Global EITI Conference in June 2023. | The tasks required for implementation of recommendations from the EITI Reports and validation, as well as the recommendations of all stakeholders, have been formulated | Recommendations of the EITI Report and validation have been implemented | The EITI MG, National Secretariat; | Until the end of July 2023 | Does not require additional financing | N/A
Monitoring and evaluation of the EITI implementation in Ukraine. | EITI requirements | Review of the monitoring and evaluation of EITI implementation in Ukraine. | Monitoring and evaluation of the EITI implementation in Ukraine has been agreed by the EITI MG and published | Monitoring and assessment of the EITI implementation in Ukraine has been published | The EITI MG, National Secretariat, DixiGroup | Until the end of December 2023 | Does not require additional financing | N/A
Financing of the EITI process in Ukraine |  | According to the rules of the Standard, the country is obliged to make the EITI process part of its domestic policy minimizing the external support. To this end, it is necessary to provide funding for publication of the Report, for the national EITI Secretariat, as well as for strengthening the institutional capacity of the Ministry to draft the Report. The following activities are proposed: 1) Financing the services of EITI Independent Administrator for preparation of the EITI Report and operation of the EITI online platform. 2) Strengthening of the structural subdivisions of the Ministry of Energy, which are responsible for ensuring transparency in the extractive industries and operation of the EITI online platform. 3) Cooperation with the World Bank and other organizations to support the EITI National Secretariat, functioning of the EITI online platform (hosting, domain, etc.), translation of the 2020 EITI Report, preparation of EITI Reports, etc. | Provision of EITI the financing (Report and online platform) from the State Budget and/or support received from the World Bank, GIZ and other donors. Attracting financing for activities of the Head of the National Secretariat | Drafting and publication of the report are carried out at the expense of the State Budget. The online platform works safely, modification of individual modules | Ministry of Energy, the EITI MG, National Secretariat | Until December 2023 | Does not require additional financing | N/A
Holding a conference "10 years of EITI implementation in Ukraine: achievements and prospects"
1.4. Capacity building for the EITI stakeholders
Measures to enhance the capacity of the EITI MG, the National Secretariat and other stakeholders | EITI requirement | The National Secretariat is developed organizationally and can provide support to the EITI MG functioning. | The National EITI Secretariat continues to function in support of the EITI MG | The operational capabilities of the EITI in Ukraine have been strengthened | Ministry of Energy, National Secretariat | Until August 2023 | International donors | 11700
| EITI requirement 1.5.c-i | Workshops and trainings conducted for stakeholders (government, companies, public, mass media, regional stakeholders) in order to strengthen their capacity and eliminate potential obstacles to the effective EITI implementation. | All parties are actively involved in the process of implementing the EITI | Members of the EITI MG are able perform their duties | The EITI MG, National Secretariat | Until the end of the year | GIZ, MF "Renaissance", USAID, DixiGroup
| EITI requirement 8.c | Trainings on using the EITI online platform | At least two trainings have been held for representatives of business entities and at least one for the public | Representatives of companies and the public have been informed about the new possibilities of using the EITI Portal for submitting and analyzing reports. | Ministry of Energy, GIZ, NGO NOVA Energy | June-November 2023 | GIZ | 1000
| EITI requirement 8.b | Involvement of representatives of the EITI stakeholders to participate in the Strategic Session on development of the EITI Portal | An event has been held for the members of the EITI MG and the Ministry of Energy | The action plan for ensuring operation of the EITI Portal for 2023-2025 includes vision and proposals from all stakeholders | Ministry of Energy, GIZ, NGO NOVA Energy | October 2023 | GIZ | 1500
|  | Conducting elections of representatives of the EITI multi-stakeholder group in accordance with the requirements of the new version of the Regulations. | All parties are actively involved in the MSG elections process | 15 selected EITI MSG members | The EITI MG, National Secretariat | Octoder-November 2023 | Does not require additional financing | N/A
Approval of the new composition of the EITI MSG in compliance with the principles of gender equality for a period of 3 years.
| EITI requirement 1.5.c-i | Preparation of the EITI MSG organizational development plan for 2023-2024.
Measures to strengthen partnerships at the international level | EITI requirements | 1. Consultations with the International EITI Secretariat, participation in the Global Conference and online meetings of the EITI Board in 2023. 2. Sharing of experience in creating the EITI MG in mining regions and conducting monitoring and evaluation of the EITI implementation. 3. Cooperation with NGOs of the implementing countries regarding the disclosure of contracts. 4. Holding an international meeting of the PWYP Regional Coalition. 5. Analysis of Ukrainian policies and legislation regarding gender equality in the mineral resources management | All parties are actively involved in the process of implementing the EITI | The operational capabilities of EITI at the international level have been strengthened | The EITI MG, National Secretariat, Association "EnergoTransparency", MF "Renaissance", DixiGroup | Until the end of the year | GIZ, MF "Renaissance", the EITI International Secretariat, USAID | 15000
| EITI requirements | Participation of the representatives of Ukraine in the workshop for representatives of the EITI National Secretariats on preparation of the national EITI work plans for 2024 with a focus on preparation for implementation of the new requirements of the EITI Standard | First draft and recommendation of the national EITI work plans for 2024
| EITI requirements | Prepare an organizational development plan to share experience with national secretariats and EITI MSG in the region.
2. National priority: strengthening partnerships between the national government, local self-governments, companies and local communities to reduce tensions
2.1. Outreach in the regions
EITI as a platform to improve partnerships between the national government, local self-governments, companies and local communities |  | Active work in the regions to create partnerships is continued, new topics for cooperation identified, in particular, creation of the regional EITI MG and holding of meetings. | A number of activities have been carried out, the public and companies are involved in the EITI implementation in the regions. | A partnership established between the government, local self-government bodies, companies and local communities | The EITI MG, National Secretariat, GIZ, MF "Renaissance" | During the year | GIZ, MF "Renaissance"
|  | Involvement of representatives of mining companies engaged in mining in the relevant territory covered by the EITI Reports as well as civil society institutions (with OGP) in the implementation of EITI in the regions where mineral extraction is carried out | Involvement of representatives of mining companies engaged in mining in the relevant territory, as well as civil society institutions, in the EITI implementation in the mining regions of Ukraine is ensured | Expanding the audience that understands the need to comply with the EITI Standard in Ukraine | Ivano-Frankivsk, Lviv, Poltava, Sumy, Kharkiv, and Chernihiv regional state administrations, Ministry of Energy | Until December 2023 | International organizations (by agreement), MF "Renaissance", Dixie Group, GIZ, Association "EnergoTransparency"
2.2. Effective implementation of the communication strategy
Ensuring broad public debate on the Report's findings, ensuring its comprehensive dissemination and discussion. Raising the awareness of all stakeholders regarding the Report's findings. | EITI requirement 7.1 | Presentation of the eighth EITI report, organizing its broad discussion | The target audience (TA) is better informed about the Report's findings | TA has the information presented in the Report and understands the meaning of the data published | Ministry of Energy, the EITI MG, National Secretariat; | February 2023 | MF "Renaissance", GIZ, USAID | 1000
|  | Translation of the EITI Report for 2021 into English and preparation of a video based on the EITI Report for 2021 both in the Ukrainian and the English languages | The Report has been translated. Video published and presented at events | Information about the EITI is available to a wide circle of people | National Secretariat | Until June 2023
Development of the EITI website to disseminate information about the process and results of its implementation |  | Support of the official site of EITI in Ukraine (support and hosting). Funding and administration of the website eiti.org.ua | The official website of the EITI in Ukraine contains complete and up-to-date information about the Initiative and is user friendly. | Information about the EITI is available to a wide circle of people | National Secretariat | Until December 2023 | MF "Renaissance", Dixie Group at the expense of USAID | 1500
|  | Publication of information on the EITI implementation on the Ministry of Energy's website | Information about meetings of the EITI MG, meetings, events | Information about the EITI is available to a wide circle of people | Ministry of Energy | During the year | Does not require additional financing | N/A